## Sep 19 - Sep 26, 2022 (hidden)
Sep 19 - Sep 26, 2022
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
All | Meeting | Weekly team meeting on Sep 23, 2022 | Discussed topics such as our tech stack, and filled out our vision doc, and prepared our questions for Dr.Mayne for out meeting with her | 1 | 1 | Done
Erika, Robby, Ayo | Learning | Look into technology stack to use for this project | Look into React | 3 |  |  | Done after meeting
Alberto | Learning | Look into alternative ways of building the site, hopefully ones that will not require TCU IT | I have a suspiscion that Dr. Mayne will be fuzzy with the requirements, so I need to be prepared to guide her through her options | 1 |  |  | Done after meeting

## Sep 26 - Oct 3, 2022 (hidden)
Sep 26 - Oct 3, 2022
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
All | Meetiing | w/ Dr.Mayne | Our first meeting with the client | 2 | 0.5 | done | filled out the interview doc
Erika RD | Tech stack | work on familarizing with proposed tech stack | Got information on the pros and cons of specific databases to use with React, did a walkthrough tutorial on "getting started with React" | 3 | 1.5 (so far) | in progress
| Documentation | Re-organize use case doc with updated format | Since we had to change the order of pages, correctly input indexes into TOC at the beginning of the use-case document | 0.5 |  | in progress
Ayo | Tech stack | work on familarizing with proposed tech stack | worked/started on the react tutorial | 3 | 0.5 | in progress
Robby | Tech stack | work on familarizing with proposed tech stack | React hands-on project- apartment finding with a map API | 2 | 2 | done
Alberto Gaucin | housekeeping | Set up CI/CD pipeline | Vercel, github, jenkins | 3 | 2 | done
Alberto Gaucin | Deliverables | Fill out Glossary | After the meeting, need a consensus on words we use | 2 |  | done
All | Deliverables | Fill out Use Case Doc | After the meeting, need at least 5 use cases | 2 | pending

## Oct 3 - Oct 10, 2022 (hidden)
Oct 3 - Oct 10, 2022
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Ayo | Documentation | Wireframes | In Balsamic, created the wireframes for the project | 2 | 1 | done | what a g
Erika RD | Documentation | Polish wireframes | Polish the balsamic wireframes | 1 | 0.5 | done
Erika RD, Alberto, Robby | Documentation | Review wireframe | Team review of wireframe material. | 1 | 2 | done
Robby | Documentation | Check vision and use case document | review vision and use case document | 0.5 | 0.5 | done
Alberto | Procedural | Meeting minutes fillout | Filled out the meeting minutes | 1 | 1 | done

## Oct 10 - Oct 17, 2022 (hidden)
Oct 10 - Oct 17, 2022
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto | Documentation | first iteration plan | Divvying up the tasks for the MVP, first iteration | 2 | 2 | Done | It is in another sheet in the Senior Design Project
All | Meeting | Dr.Mayne weekly meeting | Our planned weekly Friday meeting in her office | 1 | 0.5 | Completed | meeting details in meeting minutes
Erika | Documentation | Edit wireframes | After meeting with Dr. Mayne, she wants a couple changes implemented. I added these to the wireframes we had. | 1 | 1.5 | Completed | Updated wireframes are ready to go
Erika | Documentation | Add First Iteration project plan, finalize Release Plan document | Get our documentation filled in and ready to go for submission. | 0.5 | 1 | In progress
Ayo | Documentation | Edit Use Cases | Added additional use case from meeting with Dr. Mayne | 0.5 | 0.5 | Completed
Robby | Documentation | edit use cases |  | 0.5 | 0.5 | Completed

## Oct 18 - Oct 24, 2022 (hidden)
Oct 18 - Oct 24, 2022
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Erika R.D. | Presentation prepwork | Make the powerpoint for the IAB presentation | To make a powerpoint with information to present tot eh IAB this upcoming Friday. | 2 | 2.75 | Complete | Created using (1) Dr. Mayne's grant proposal, (2) Dr. Mayne's presentation to us, (3) TES Wireframe design and current implementation plans (4) The OSU NALA website.
Ayo | Documentation | someone really needs to re-do the wireframes with Dr. Mayne's comments on having a start page OTHER than the map. ~erika | Implenting Dr. Mayne's comments to the wireframes | 2 | 3 | Complete | Implemented comments from Dr. Mayne
Ayo | Documentation | Vision Document | Adding more information to the vision doc | 1 | 1.5 | Complete
Alberto Gaucin | Documentation | Glossary | Tidy up the Glossary description | 0.5 | 0.5 | Complete | It was never really empty, I just forgot to erase the blue parts, and I added some terms as well
Alberto Gaucin | Documentation | Vision Document | Tidy up the Vision Doc | 2 | 2 | Complete | Just minor adjustments based on comments
Robby Dai | Documentation | Iteration plan 1 | Finish iteration plan 1 | 1 | 1 | Complete
Robby Dai | Documentation | Use case | Update use case based on Dr. Mayne's comments | 1 | 1.5 | Complete

## Oct 25 - Oct 31, 2022 (hidden)
Oct 25 - Oct 31, 2022
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Erika R.D. | Presentation | Edit powerpoint, practice for presentation to IAB | Write out an outline of what to say, practice a two-minute presentation, and deliver it to the IAB. Fix slides accordingly. | 3 | 3 | Complete | Wish I had practiced more! But things turned out okay.
Ayo | Wireframes | Edit wireframes | Edit and presented wireframes to team | 0.5 | 0.5 | Complete
Alberto Gaucin | Presentation | Consult with Erika | Go over the presentation materials to cover for IAB | 0.5 | 1 | Complete
Alberto Gaucin | Meeting | Stand-up | Led team in the meeting, shared github repo and firebase database | 1 | 1 | Complete
Robby | Documentation | Edit use cases | update use cases list | 0.5 | 0.5 | Complete
All | Documentation | Iteration plan 1 | self assign tasks in iteration plan 1 | 0.5 | 0.5 | Complete

## Nov 1 - Nov 6, 2022 (hidden)
Nov 1 - Nov 7, 2022
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto Gaucin | Coding | skeleton | Prepare some frontend functionality for the meeting on Friday | 6 | 6 | done
Erika R.D. | Documentation | SRS, Use case polishing | Final version of use case, make SRS, make sure all other documents are ready to go. | 3 |  | In progress
Ayo | Database | Firebase | Setting the firebase database and filling with mock data | 2 |  | In progress
Robby | Coding | Sign-in page | Create sign in page and set authentication | 3 | 3 | Done

## Nov 7 - Nov 13, 2022 (hidden)
Nov 7 - Nov 13, 2022
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Erika RD | Development | Make instructor tools page | Add the instructor/educational materials PDF's holder page. | 1 |  | in progress
Erika RD | Documentation | Revise Use Cases for e-valuate | Revise Use Cases for e-valuate | 1 | 0.5 | complete - for now.
Robby Dai | Documentation | Revise Use Cases for e-valuate | Revise Use Cases for e-valuate | 2 | 2 | in progress | Need to keep checking for any use cases that need to be added
Robby Dai | Development | Test sign-in page | Test sign-in page and authentication | 0.5 | 0.5 | in progress
Alberto Gaucin | Coding | Code some more | test map and home page | 3 | 3 | done
Alberto Gaucin | Documentation | Revise Use Cases for e-valuate | Revise Use Cases for e-valuate | 1 |  | in progress
Ayomide A | Documentation | Revise Use Cases for e-valuate | Revise Use Cases for e-valuate | 2 | 2 | in progress
Ayomide A | Documentation | Creating a database schema | Making a database schema/logical data model to add to srs | 1 | 0.5 | in progress

## Nov 14 - Nov 20, 2022 (hidden)
Nov 14 - Nov 20, 2022
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Ayomide A | Documentation | Filling out the SRS | Filling out the SRS doc | 2 | 1.5 | in progress
Alberto Gaucin | Coding | Fix admin bug | Figure out why auth is not connecting | 1 |  | in progress
Alberto Gaucin | Coding | CRUD implementation | CRUD for admin dashboard | 5 |  | in progress
Robby Dai | Development | Fix sign in page |  | 2 | 2

## Nov 21 - Nov 27, 2022 (hidden)
Nov 21 - Nov 27, 2022
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto Gaucin | Documentation | FInish the SRS | Fill out the rest of the SRS | 1 | 1 | Complete
Alberto Gaucin | Coding | Code some more | Continuing to work on page design, crud | 5 |  | in progress

## Nov 28 - Dec 4, 2022
Nov 21 - Nov 27, 2022
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Erika RD | Presentation | Make the slides for Monday's presentation in class | make slides to comply with the necessary information we will be presenting in class on Monday | 1 | 1.5 | in progress
Erika RD | Development | Connect to database | connect OUR project implementation to the firebase database | 1 | 5 | in progress | this was unnecessarily difficult
Erika RD | Development | Fetch PDF's from database | Fetch from firebase and successfully display PDF files on our site | 2 | - | in progress
Erika RD | Development | Fetch meteorite information | Fetch meteorite information from firebase to our page | 2 | - | in progress
Ayomide | Development | Popup Modal | Popups to display the meteorite information | 2 | 4 | testing
Robby Dai | Development | Implement add meteorite feature | Let user add meteorite after signing in | 2 | 3 | in progress
Alberto Gaucin | Development | Testing | Test the current functionality | 3 | 3 | in progress

## Jan 16- Jan 22, 2023
January 16th - January 22nd, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto Gaucion | Coding | Work on source code | Added some more flair to the overall presentation, I am not going to wait for that one person | 6 | 6 | In progress
Erika Diaz | Coding | Try to fix the UI Hydration Issue, connect to Firebase again | Troubleshooting on hydration issue in firebase, fix image source and alter image location | 2 | 3 | Resolved (not fixed though)
Ayomide | Coding | Firebase-React Hydration | Looked into different reasons why we had problems with the hydration - came to the conclusion that it wasn't a problem with react (YAY) | 2 | 2 | In progress
Robby Dai |  | Redesign admin dashboard | Redesigned admin dashboard for the two tables | 1 | 1 | In progress

## Jan 23- Jan 29, 2023
January 23rd - January 29th, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Ayomide A | Documentation | Test Cases | Made a test case for dr. Mayne to use when testing the map | 1 | 0.5 | In progress | Not super sure about the format but still working on it
Robby Dai | Coding | Admin CRUD | Implement admin CRUD | 3 | 3 | In progress
Erika RD | Documentation | Meeting Agenda, Test Cases | Meeting Agendas for meeting with Dr. Wei, Dr. Mayne (Client) | 1 | 1 | Completed
Erika RD | Test Cases | Test cases | worked on test cases for Dr. Mayne to try | 1 | 0.5 | In progress
Alberto | Coding | Map api call | Work on implementing mapbox and google maps api | 4 | 4 | completed

## Jan 30- Feb 5, 2023
January 30th - Feburary 5th, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Erika RD | Meeting Management | Make meeting agendas | Made meeting Agendas for our meeting with Dr. Wei, Dr. Mayne, and our designer for this next week of Feb 6th | 1 | 1 | Complete | Designer agenda can be found under Dr. Mayne's meeting agenda document for this next week
Erika RD | Documentation | Updates to use case document | Making edits according to the newest implementation and design of our program. Re-evlauating current explanation and flow of our use cases. | 1 | 1 | In progress | To be continued as development continues
Erika RD | Research & outreach | reached out to a potential support/mentor site | Native Land is a site dedicated to depicting Native Lands accurately on maps. They have an API, and support initiatives such as ours in bringing Native visibility to technology. They may be able to help us with the map development portion of outlining Native Lands without paying for Google API. I reached out. | 0.25 | 0.25 | Complete/In progress | waiting for a response
Ayomide A | Testing | Test Cases | Updating test cases & going through to make sure they correctly align with use cases/client neededs | 2 | 1 | In progress
Alberto Gaucin | Coding | Coding | the admin panel now adds tools and shows data | 3 | 3 | completed
Robby Dai | Coding | Coding | start implement edit and delete function for meteorites in admin panel | 2 | 2 | in progress

## Feb 6 - Feb 12, 2023
February 6th - February 12th, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto Gaucin | Coding | Coding | the admin panel now deletes and edits | 5 | 5 | in progress
Erika Rebollo Diaz | Organization | Meeting Agendas, team communications | make and print meeting agendas for designer meeting, client meeting, and Dr. Wei's weekly meeting | 2 | 1.5 | Complete
Erika Rebollo Diaz | Meeting Communications | Lead designer introduction meeting | Lead first meeting with designer, take thorough notes, and make sure all questions are answered to the best of our abilities | 1 | 1 | Complete
Ayomide Ayowole-Obi | Test Cases | Updating test cases | making sure the test cases reflect new changes | 1 | 1 | in progress
Robby Dai | Coding | Coding | implement delete and edit function for educational tools | 2 | 2 | in progress

## Feb 13 - Feb 19, 2023
February 13th - February 19th, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto Gaucin | Coding | Finish funcitonality on admin panel and move meteorite filter | Finish funcitonality on admin panel and move meteorite filter | 5 | 5 | In progress
Erika Rebollo Diaz | Organization | Meeting Agendas, team communications | make and print meeting agendas for designer meeting, client meeting, and Dr. Wei's weekly meeting | 1 | 1 | Complete
Erika Rebollo Diaz | Meeting Communications | Lead designer meeting, weekly meeting | Lead meetings with designer, take thorough notes, and make sure all questions are answered to the best of our abilities | 1 | 1 | Complete
Ayomide Ayowole-Obi | Test Cases | Updating test cases | making sure the test cases reflect new changes | 1 | 1 | in progress
Ayomide Ayowole-Obi | Client & Designer communication | Mantaining contact with our client and designer | Continously emailing and mantianing contact with our client and designer on upcoming tasks, design updates, and feature change requests | 1 | 1 | Always in progress
Robby Dai | Coding | Working on adding files on admin page | Working on adding files on admin page | 2 | 2 | in progress

## Feb 20 - Feb 26, 2023
February 20th - February 26th, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto Gaucin | Coding | Finish funcitonality on admin panel and move meteorite filter | Finish funcitonality on admin panel and move meteorite filter | 5 | 5 | In progress
Erika Rebollo Diaz | Organization | Meeting Agendas, team communications | make and print meeting agendas for designer meeting, client meeting, and Dr. Wei's weekly meeting | 1 | 1 | Complete
Erika Rebollo Diaz | Meeting Communications | Lead designer meeting, weekly meeting | Take thorough notes, and make sure all questions are answered to the best of our abilities | 1 | 1 | Complete
Erika Rebollo Diaz | Planning | Create Task Manager/To-Do spreadsheet to track our project completion progress | Create a task manager so we can track every single little item that we still have left to implement. This is to be used as a Master overview to know who needs to get what done, as well as the priority level of each item | 0.5 | 1 | Complete
Ayomide Ayowole-Obi | Test Cases | Updating test cases | making sure the test cases reflect new changes | 1 | 1 | in progress
Ayomide Ayowole-Obi | Client & Designer communication | Mantaining contact with our client and designer | Continously emailing and mantianing contact with our client and designer on upcoming tasks, design updates, and feature change requests | 1 | 1 | Always in progress
Robby Dai | Coding | Fix the bug that meteorites are at the correct locations on map | Fix the bug that meteorites are at the correct locations on map | 2 | 2 | in progress

## Feb 27 - Mar 5, 2023
February 27th - March 5th, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto Gaucin | Coding | Finish funcitonality on admin panel and move meteorite filter | Finish funcitonality on admin panel and move meteorite filter | 5 | 5 | In progress
Erika Rebollo Diaz | Organization | Meeting Agendas, team communications, Update checklist | Mantain prioritization checklist, make and print meeting agendas for designer meeting, client meeting, and Dr. Wei's weekly meeting | 1 | 1 | Complete
Erika Rebollo Diaz | Meeting Communications | Lead designer meeting, weekly meeting | Take thorough notes, and make sure all questions are answered to the best of our abilities | 1 | 1 | Complete
Ayomide Ayowole-Obi | Test Cases | Updating test cases | making sure the test cases reflect new changes | 1 | 1 | in progress
Ayomide Ayowole-Obi | Client & Designer communication | Mantaining contact with our client and designer | Continously emailing and mantianing contact with our client and designer on upcoming tasks, design updates, and feature change requests | 1 | 1 | Always in progress
Robby Dai | Coding | Fix the bug that meteorites are at the correct locations on map | Cannot fix it. We use marker instead of the meteorite gif. | 2 | 2 | Complete

## Mar 6 - Mar 12, 2023
March 6th - March 12th, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto Gaucin | Coding | Finish funcitonality on admin panel and move meteorite filter | Finish funcitonality on admin panel and move meteorite filter | 5 | 5 | In progress
Erika Rebollo Diaz | Organization | Meeting Agendas, team communications, Update checklist | Mantain prioritization checklist, make and print meeting agendas for designer meeting, client meeting, and Dr. Wei's weekly meeting | 1 | 1 | Complete
Erika Rebollo Diaz | Meeting Communications | Lead designer meeting, weekly meeting | Lead first meeting with designer, take thorough notes, and make sure all questions are answered to the best of our abilities | 1 | 1 | Complete
Ayomide Ayowole-Obi | Test Cases | Updating test cases | making sure the test cases reflect new changes | 1 | 1 | in progress
Ayomide Ayowole-Obi | Client & Designer communication | Mantaining contact with our client and designer | Continously emailing and mantianing contact with our client and designer on upcoming tasks, design updates, and feature change requests | 1 | 1 | Always in progress
Robby Dai | Organization | Organizeing the infomation from client. | organize the information from out client. Convert the coordinates of meteorites so that we can put them into the map | 2 | 2 | in progress

## Mar 13 - Mar 19, 2023
March 13th - March 19th, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto Gaucin | Coding | Finish funcitonality on admin panel and move meteorite filter | Finish funcitonality on admin panel and move meteorite filter | 5 | 5 | In progress
Erika Rebollo Diaz | Organization | Meeting Agendas, team communications, Update checklist | Mantain prioritization checklist, make and print meeting agendas for designer meeting, client meeting, and Dr. Wei's weekly meeting | 1 | 1 | Complete
Erika Rebollo Diaz | Design Elements | Create graphics for the site to use | Since we don't have access to any images, we need filler graphics to fill-in the site while our client processes her images. | 1 | 2 | In progress
Ayomide Ayowole-Obi | Test Cases | Updating test cases | making sure the test cases reflect new changes | 1 | 1 | in progress
Ayomide Ayowole-Obi | Client & Designer communication | Mantaining contact with our client and designer | Continously emailing and mantianing contact with our client and designer on upcoming tasks, design updates, and feature change requests | 1 | 1 | Always in progress
Robby Dai | Coding | Coding based on feedback | Coding based on clients' feedback after she going through the use cases | 2 | 2 | in progress

## Mar 20 - Mar 26, 2023
March 20th - March 26th, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto Gaucin | Coding | Finish funcitonality on admin panel and move meteorite filter | Finish funcitonality on admin panel and move meteorite filter | 5 | 5 | In progress
Erika Rebollo Diaz | Organization | Meeting Agendas, team communications, Update checklist | Mantain prioritization checklist, make and print meeting agendas for designer meeting, client meeting, and Dr. Wei's weekly meeting | 1 | 1 | Complete
Erika Rebollo Diaz | Design Elements | Create graphics for the site to use | Since we don't have access to any images, we need filler graphics to fill-in the site while our client processes her images. | 1 | 2.5 | In progress
Ayomide Ayowole-Obi | Test Cases | Updating test cases | making sure the test cases reflect new changes | 1 | 1 | in progress
Ayomide Ayowole-Obi | Client & Designer communication | Mantaining contact with our client and designer | Continously emailing and mantianing contact with our client and designer on upcoming tasks, design updates, and feature change requests | 1 | 1 | Always in progress
Robby Dai | Testing | Testing all the features of the main website | Testing all the features of the main website. Fixing bugs or making changes after testing. | 2 | 2 | Complete

## Mar 27 - Apr 2, 2023
March 27th - April 2nd, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto Gaucin | Coding | Finish funcitonality on admin panel and move meteorite filter | Finish funcitonality on admin panel and move meteorite filter | 5 | 5 | In progress
Erika Rebollo Diaz | Organization | Meeting Agendas, team communications, Update checklist | Mantain prioritization checklist, make and print meeting agendas for designer meeting, client meeting, and Dr. Wei's weekly meeting | 1 | 1 | Complete
Erika Rebollo Diaz | Design Elements | Update mission statement graphic, map-marker gif, etc... | Continued to create filler graphics for the site. | 1.5 | 3 | In progress
Erika Rebollo Diaz | Site Content | Generating bio's for all our team members | Have something to write for our team in our site | 0.5 | 1 | In progress
Ayomide Ayowole-Obi | Test Cases | Create document for Client Demo walkthrough with Dr. Wei | Create a checklist for uniquely walking through every necessary test case at our demo client meeting | 1 | 3 | in progress
Ayomide Ayowole-Obi | Client & Designer communication | Mantaining contact with our client and designer | Continously emailing and mantianing contact with our client and designer on upcoming tasks, design updates, and feature change requests | 1 | 1 | Always in progress
Robby Dai | Testing | Testing admin page | Testing admin page. Fixing bugs or making changes after testing. | 2 | 2 | Complete

## Apr 3 - Apr 9, 2023
April 3rd - April 9th, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Alberto Gaucin | Coding | Finish funcitonality on admin panel and move meteorite filter | Finish funcitonality on admin panel and move meteorite filter | 5 | 5 | In progress
Erika Rebollo Diaz | Make poster | Make the poster for SRS Presentation | Incorporate design and text elements into poster for SRS | 2 | 7 | Complete
Erika Rebollo Diaz | Design Elements | Graphics design upkeep | Continue to edit and create graphics according to updated client needs | 1 | 2 | In progress
Erika Rebollo Diaz | Organization | Meeting Agendas, team communications, Update checklist | Mantain prioritization checklist, make and print meeting agendas for designer meeting, client meeting, and Dr. Wei's weekly meeting | 1 | 1 | Complete
Erika Rebollo Diaz | Documentation | Fill in WAR, updates to Documentation for final review | Fill in WAR, updates to Documentation for upcoming final review and submission | 1 | 2 | In progress
Ayomide Ayowole-Obi | Documentation | Fill in WAR, updates to Documentation for final review | Fill in WAR, updates to Documentation for upcoming final review and submission | 1 | 2 | In progress
Ayomide Ayowole-Obi | Communication | Obtain profile images from all contributors outside of TCU | Reach out to all involved parties via email to obtain their bio information and images to include in site | 1 | 2 | In progress
Ayomide Ayowole-Obi | Client & Designer communication | Mantaining contact with our client and designer | Continously emailing and mantianing contact with our client and designer on upcoming tasks, design updates, and feature change requests | 1 | 1 | Always in progress
Erika Rebollo Diaz | Site Content | Generating bio's for all our team members | Have something to write for our team in our site | 1 | 1 | Pending approval
Robby Dai | Coding | Making changes based on Dr. Mayne's feedback | Making changes based on Dr. Mayne's feedback | 2 | 2 | In progress

## Apr 10 - Apr 16, 2023
April 10rd - April 16th, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Erika Rebollo Diaz | Finalize Documentation | Review and finalize all documentation | Reviewed and made final edits to Introductory meeting minutres, Glossary, Vision, and Software Requirements document | 1 | 1 | Complete
Ayomide Ayowole-Obi | Finalize Documentation | Review and finalize documentation | Review and update Use Cases document for accuracy before submission | 1 | 1 | Complete
Erika Rebollo Diaz | Graphics | Finalize graphics for the website | Bio images, etc... all ready to go for delivery date | 1 | 1 | Complete
Erika Rebollo Diaz | SRS Poster | Finalize SRS Poster, export and share accordingly | Add QR Code, make final edits to the poster for SRS poster submission | 1 | 2 | Complete
Robby Dai | Coding | Landing page | Finish landing page for our project | 2 | 2 | Complete
Alberto Gaucin | Coding | UI changes | Implementing the touch ups to the UI that Dr.Mayne said | 2 | 2 | Complete

## Apr 17 - Apr 22, 2023
April 10rd - April 16th, 2023
Team Member | Task Categories | Planned Task | Description | Planned Hours | Actual Hours | Status | Comments
Erika Rebollo Diaz | Finalize Documentation | Review and finalize all documentation | Reviewed and made final edits to Introductory meeting minutres, Glossary, Vision, and Software Requirements document | 1 | 1 | Complete
Ayomide Ayowole-Obi | Presentation | Create rough draft final presentation | Created and designed a rough draft for the presentation | 1 | 1 | Complete
Erika Rebollo Diaz | Graphics | Finalize graphics for the website | Bio images, etc... all ready to go for delivery date | 1 | 1 | Complete
Erika Rebollo Diaz | SRS Poster | Finalize SRS Poster, export and share accordingly | Add QR Code, make final edits to the poster for SRS poster submission | 1 | 2 | Complete
Robby Dai | Presentation | Prepare for presentation | Prepare for presentation | 2 | 2 | Complete
Alberto Gaucin | Coding | UI changes | Implementing the touch ups to the UI that Dr.Mayne said | 2 | 2 | Complete